## Year 1 Action Plan
Theme | Reference | Action | Lead | Key stakeholders | Strategic alignment | Timescales
Aim 1: Ensure inclusive access for all | A1.1 | Support the planning authority in providing feedback to the London wide Greenbelt Review. | Planning | Greenspaces | Local Plan Parks and Open Spaces Strategy - SC1.1 | Short Term
Aim 1: Ensure inclusive access for all | A1.2 | Review opportunities for inclusive design in the redevelopment of Heybourne Park playground | Greenspaces | Notting Hill Genesis | Parks and Open Spaces Strategy - SC1.2 | Short Term
Aim 1: Ensure inclusive access for all | A1.3 | Provide feedback to CST in relation to proposed new/extension PSPO implementation. | Community Safety Team | Greenspaces | Parks and Open Spaces Strategy - SC1.3 | Short Term
Aim 1: Ensure inclusive access for all | A1.4 | Review opportunities and initiatives to enhance reporting of environmental crime and safety, linked to partner campaigns. | Greenspaces | Streetscene, Community Safety, Metropolitain Police | Parks and Open Spaces Strategy - SC1.3 | Short Term
Aim 1: Ensure inclusive access for all | A1.5 | Target investment in areas that exhibit lower condition and functionality scores – removing, repairing or replacing items that are in most need. | Greenspaces | Residents, Community Groups, Friends Groups | Parks and Open Spaces Strategy - SC1.2 & SC2.2 | Short Term
Aim 1: Ensure inclusive access for all | A1.6 | Deliver Park Patrols at identified locations during summer period, exlporing financially sustainable options for long term delivery. | Greenspaces | Community Safety Team | Parks and Open Spaces Strategy - SC1.3 | Short Term
Aim 1: Ensure inclusive access for all | A1.7 | Work with the Barnet Greenspaces Network to establish a ‘Barnet Safer Parks Principles’; a set of principles to enhance access, promote safety and equity. | Greenspaces |  | Parks and Open Spaces Strategy - SC1.3 | Short term
Aim 1: Ensure inclusive access for all | A1.8 | Work with partners/key stakeholders to improve safety and accessibility eg through targeted communications such as fire safety (eg BBQs.) | Greenspaces | Community Safety Partnership Board, Community Saftey Team | Parks and Open Spaces Strategy - SC1.3 | Short term
Aim 1: Ensure inclusive access for all | A1.9 | Work to increasing the number of Green Flag Awards working in partnership with the Barnet Greenspaces Network. | Greenspaces | Friends Of Groups, Community Organisations |  | Short Term
Aim 1: Ensure inclusive access for all | A1.10 | Create a matrix of stakeholders for all parks and open spaces across the borough | Greenspaces | Friends Of Groups, Community Organisations | Parks and Open Spaces Strategy - SC4.1 & SC4.3 | Short Term
Aim 2: Support health, wellbeing and active lifestyles | A2.1 | Work in partnership with the LTA / community partners to co-ordinate activities in relation to Great British Tennis Week 2026. | Sport and Physical Activity Team | Greenspaces | Fit and Active Framework Parks and Open Spaces Strategy - SC2.1 | Short Term
Aim 2: Support health, wellbeing and active lifestyles | A2.2 | Work in partnership with community stakeholders/organisations to promote activities such as Parkrun and Swing Fitness | Sport and Physical Activity Team | Greenspaces | Fit and Active Framework Parks and Open Spaces Strategy - SC2.1 | Short Term
Aim 2: Support health, wellbeing and active lifestyles | A2.3 | Work in partnership with the Sanctuary Team to promote parks and open spaces. | Sport and Physical Activity Team | Greenspaces | Fit and Active Framework Parks and Open Spaces Strategy - SC2.1 | Short Term
Aim 2: Support health, wellbeing and active lifestyles | A2.4 | Work with Public Health to match participants trained by the 'Barnet Community Food Growing Network - Leadership Programme' with community food growing spaces in the borough | Greenspaces, Public Health | Incredible Edible Barnet | Barnet Food Plan Parks and Open Spaces Strategy - SC2.2 | Short Term
Aim 2: Support health, wellbeing and active lifestyles | A2.5 | Fund supervised drop in community food growing sessions within council owned food growing spaces and parks | Greenspaces, Public Health | Incredible Edible Barnet | Barnet Food Plan Parks and Open Spaces Strategy - SC2.2 | Short Term
Aim 2: Support health, wellbeing and active lifestyles | A2.6 | Work in partnership with Notting Hill Genesis to deliver initial phase park improvements at Heybourne Park | Greenspaces | Notting Hill Genesis | Parks and Open Spaces Strategy - SC2.3 | Short Term
Aim 2: Support health, wellbeing and active lifestyles | A2.7 | Work in partnership with Regal London to deliver improvements at Glebelands Open Space | Greenspaces | Sport and Physical Activity Team / Regal London | Parks and Open Spaces Strategy - SC2.3 | Short Term
Aim 2: Support health, wellbeing and active lifestyles | A2.8 | Deliver Phase 1 improvements at West Hendon Playing Fields | Greenspaces | Football Foundation, Sport England, Planning, Estates | Parks and Open Spaces Strategy - SC2.3 | Short Term
Aim 2: Support health, wellbeing and active lifestyles | A2.9 | Work with the Growth Team to review emerging development pipeline proposals in Mill Hill and East Finchley, including play requirements. | Greenspaces | Growth Team, Planning, Biodiversity | Parks and Open Spaces Strategy - SC2.3 | Short Term
Aim 2: Support health, wellbeing and active lifestyles | A2.10 | Work with partners through the Fit and Active Barnet network to promote new and existing in ways in which our parks can be used as a resource for improving health and wellbeing. | Sport and Physical Activity Team | Greenspaces, Fit and Active Barnet Partnership Board |  | Short term
Aim 3: Promote environmental sustainability and nature recovery | A3.1 | Use the updated baseline data, SINC Network and Nature Recovery Review and Local Nature Recovery Strategy to inform the emerging Local Nature Recovery Plan for Barnet. | Greenspaces (Biodiversity) | Planning | London-wide LNRS Parks and Open Spaces Strategy - SC3.1 | Short Term
Aim 3: Promote environmental sustainability and nature recovery | A3.2 | Continue to develop sustainable horticultural practices e.g. using peat-free compost, non-plastic membranes when planting and adding rain water capture to park buildings. | Greenspaces | Grounds Maintenance | Climate action scorecard Parks and Open Spaces Strategy - SC3.2 | XX
Aim 3: Promote environmental sustainability and nature recovery | A3.3 | Continue to explore integrated pest management and sustainable alternatives to weed management, favouring biological control and non-chemical options where appropriate, recognising the need to treat Schedule 9 species and species that impact public health eg giant hogweed and Oak Processionary Moth. | Streetscene | Greenspaces | Parks and Open Spaces Strategy - SC3.2 | Business as Usual
Aim 3: Promote environmental sustainability and nature recovery | A3.4 | Increase the biodiversity of council owned and managed grasslands by enhancing the species mix and altering the management where appropriate (e.g. by reseeding areas and changing mowing regime). Continue to add signage to these areas to inform residents. | Streetscene | Greenspaces | Parks and Open Spaces Strategy - SC3.2 | Short Term
Aim 3: Promote environmental sustainability and nature recovery | A3.5 | Fund, coordinate and promote river restoration and enhancement work on the Dollis Brook, continuing work on the Upper Dollis and gaining the necessary permission for the work downstream on the Lower Dollis. | Greenspaces | Thames21, Environment Agency | SuDs strategy, Flood Risk Management Strategy Parks and Open Spaces Strategy - SC3.4 | Short Term
Aim 3: Promote environmental sustainability and nature recovery | A3.6 | Add SuDs features in Cherry Tree Wood and Lyttelton Playing fields that contain and hold rainwater and run off eg swales and rain gardens, that also increase biodiversity. | Greenspaces | Friends Groups | SuDs strategy, Flood Risk Management Strategy Parks and Open Spaces Strategy - SC3.5 | Short Term
Aim 3: Promote environmental sustainability and nature recovery | A3.7 | Support the interventions delivered in parks as part of the Action for the Silk Stream Project, running from 2021 - 2027. | Highways | Greenspaces, Thames21 | SuDs strategy, Flood Risk Management Strategy Parks and Open Spaces Strategy - SC3.5 | Short Term
Aim 3: Promote environmental sustainability and nature recovery | A3.8 | Establish an independent Site Selection Panel to inform the process of the SINC identification, assessment and ratification. | Greenspaces (Biodiversity) |  |  | Short Term
Aim 4 :Strengthening Partnerships, Stewardship and Community Engagement | A4.1 | Install a water supply to the Tram Shed building in Montrose Park, for use by the community food growing space within the park | Greenspaces | Estates | Community Asset Strategy Parks and Open Spaces Strategy - SC4.1 | Short Term
Aim 4 :Strengthening Partnerships, Stewardship and Community Engagement | A4.2 | Reinstate the electricity supply to Mill Hill Park Keepers Building, for use by the Friends Group | Greenspaces | Estates | Community Asset Strategy Parks and Open Spaces Strategy - SC4.1 | Short Term
Aim 4 :Strengthening Partnerships, Stewardship and Community Engagement | A4.3 | Fund, coordinate and promote a series of volunteer training and engagement events at the Welsh Harp, delivering the aims of the management plan. | Greenspaces | BGSN | Parks and Open Spaces Strategy - SC4.2 | Short Term
Aim 4 :Strengthening Partnerships, Stewardship and Community Engagement | A4.4 | Continue to support the Barnet Green Space Network through the development of engagement and training plans, including habitat management and species identification training sessions. | Greenspaces | BGSN | Parks and Open Spaces Strategy - SC4.2 | Short Term
Aim 5: Sustainable investment and innovation | A5.1 | Work to bring the closed kiosk in Basing Hill Park back into use and seek to provide public toilets in the adjacent pavilion. |  | Estates, Planning | Parks and Open Spaces Strategy - SC5.1
Aim 5: Sustainable investment and innovation | A5.2 | Securing consent for the change of use of New Southgate Recreation Ground pavilion in order to create a café with public toilets alongside sports changing rooms. | Estates Team |  | Parks and Open Spaces Strategy - SC5.2
Aim 5: Sustainable investment and innovation | A5.3 | Explore the potential of funding opportunities through alternative sources such as partnerships, grants and sponsorship arrangements. |  |  | Parks and Open Spaces Strategy - SC5.3
Aim 6: Promote learning, culture and heritage | A6.1 | work with Culture and Community Participation stakeholders and artists to explore feasibility of ‘design and decorate’ selected buildings. | Culture | Greenspaces | Parks and Open Spaces Strategy - SC6.1 | Short Term
Aim 6: Promote learning, culture and heritage | A6.2 | Progress developing plans for a new Regional Park within Barnet and explore designating existing areas as Metropolitan Parks as part of a phased approach. | Greenspaces & Growth | Strategic Planning, Highways |  | Short
Aim 6: Promote learning, culture and heritage | A6.3 | Review of the events policy to ensure that it is consistent and enables future sustainability | Greenspaces (Events in Parks Team) | Residents, Community Organisations, Culture Team |  | Short Term